## Sheet1
Num | Piece | Change | Work Required | Notes | Assigned To | Status
2 | Dashboard | Take "League Average" before normalization | Low |  | Ethan | Done
3 | Dashboard | List sample size (# plays) for each player | Low |  | Ethan | Done
4 | Dashboard | Reduce axis scaling to maximum | Low |  | Ethan | Done
6 | Dashboard | Add cluster centres to league-specific charts | Low |  | Ethan | Done
8 | Dashboard | Enable zooming using mouse wheel | Low |  | Ethan | Skipped
11.5 | Dashboard | Enable exporting graphs as PNG/JPEG | Low |  | Ethan | Done
13 | Dashboard | Print most similar players | Low-Med |  | Ethan
| Dashboard | Enable table exports | Low |  | Ethan | Done
1 | Dashboard | Password-protect the Heroku link | Low |  | Arif
5 | Dashboard | Add table with cluster centre stats | Low | Maybe colour code to draw attention to the higher stats | Arif
7 | Dashboard | Add table with raw data of player stats | Low |  | Arif
9 | Dashboard | Print players with same cluster switch | Low |  | Arif
10 | Dashboard | Print 10 players per cluster | Low |  | Arif
11 | Dashboard | Filter by cluster | Low |  | Arif
12 | Dashboard | Indicate play type(s) with bigggest change per player | Low-Med
14 | Data | Collect list of player's teams/leagues per season | Medium | We think this would be valuable but need to think about this futher before diving in
15 | Dashboard | Allow filtering of dropdown by team/country/league | Medium + Low
16 | Dashboard | List seasons, teams for each player | Medium + Low
17 | Dashboard | Allow showing/hiding players by team/country/league | Medium + Low-Med
18 | Research | Generate country and league-specific confusion matrices | Medium + Low
19 | Data | Collect efficiency statistics per play type | High | We're thinking of holding back on this and leaving it for a potential future project
20 | Research | Compare efficiency for players switching clusters | High + Low-Med
21 | Research | Repeat clustering with scaled variables | Low | We're planning to add this to our eventual report
22 | Research | Clean duplicate names (e.g. Lebron vs LeBron) | Medium | Not a priority. Can use packages like Levenshtein, FuzzyWuzzy
23 | Pipeline | Scrape newer Synergy data | High | This seems like a good step to take after we finalize our report/dashboard
24 | Pipeline | Automatically parse new data | High + Low
25 | Pipeline | Automatically cluster players and add to dashboard | High + Low